## Product_Backlog
Product Name: | Baking App | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Duy Nguyen
Initials: | DN
Student ID: | 10015102
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 8 |  | Total
Sprint 1 Left | 5 | 3 | 1
Sprint 2 Left | 5 | 0 | 2
Sprint 3 Left | 5 | 0 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
SM | 1 |  | 1 | Finished in Sprint 1 | User | see recipe images in Linear Layout (vertically),GridView (horizontally) | I can choose which food to make
SR | 2 |  | 1 | Finished in Sprint 1 | User | see recipe ingredients, recipe steps | I can see the overview of my food that I gonna to make
SD | 3 |  | 1 | Finished in Sprint 1 | User | see details of food ingredients |  | create the database and content provider to store the name and ids of the user's favorite movie
SE | 4 |  | 2 |  | User | see details of each food step
RA | 5 |  | 2 |  | User | rotate a device and see a video in a full screen (video available only)
ST | 6 |  | 2 |  | User | see the beautiful display in my tablet
SI | 7 |  | 3 |  | User | see its app widget in my home screen
TA | 8 |  | 3 |  | Developer | test app using Espresso

## Sprint_01_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2018-06-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-06-10
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 20
Day 1 Left | 13 | 7
Day 2 Left | 9 | 4
Day 3 Left | 8 | 1
Day 4 Left | 8 | 0
Day 5 Left | 8 | 0
Day 6 Left | 8 | 0
Day 7 Left | 8 | 0
| Feature ID |  | Description | Status | Notes
| SM |  | Create activity_recipe.xml with toolbar and gridview | Completed Day 1 | activity_menu.xml in Tea Time project solution 4
| SM |  | Create grid_item_layout.xml for each recipe | Completed Day 1 | grid_item_layout in Tea Time project solution 4
| SM |  | Create Recipe.java to fit with json | Completed Day 1
| SM |  | Update Internet permisson & Acess Network Statein AndroidManifesr | Completed Day 1
| SM |  | Add Retrofit 2 dependency in build.Gradle | Completed Day 1
| SM |  | Create RetrofitClient.java | Completed Day 1 | RetrofitClient.java in Movie App
| SM |  | Create RecipeClient interface | Completed Day 1
| SM |  | Create RecipeMenuAdapter.java | Completed Day 2 | TeaMenuApdater in Tea Time
| SM |  | Create MainActivity.java with toolbar |  | MenuActivity.java
| SM |  | Set GridView onClickListener and pass data to
| SR |  | Create statc fragment_detail_recipe_list.xml (using listview) | Completed Day 2 | fragment_master_list.xml- https://android--code.blogspot.com/2015/08/android-listview-item-click.html
| SR |  | Create DetailRecipeListFragment.java which return a view | Completed Day 2 | MasterListFragment.java
| SR |  | Create detail_recipte_list_activity.xml containing <fragment> tag | Completed Day 2
| SR |  | Create onItemClickListener variable & interface in DetailRecipeListFragment.java | Completed Day 3 | https://android--code.blogspot.com/2015/08/android-listview-item-click.html
| SR |  | Call set on ItemClickListener in onCreateView()
| SR |  | Create RecipeListActivity.java with detail_recipte_list_activity.xml
| SD |  | Add implements ItemCliclistener to go to RecipeDetailActivity.java in RecipeListActivity.java
| SD |  | Create Recipe_ingredient_detail.xml | In Work
| SD |  | Create RecipeDetailActivity.java according to the mockup
| SD |  | pass ingredients data to RecipeDetailActivity.java(also previous and next one)

## Sprint_02_Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2018-06-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-06-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 6
Day 1 Left | 6 | 0
Day 2 Left | 6 | 0
Day 3 Left | 6 | 0
Day 4 Left | 6 | 0
Day 5 Left | 6 | 0
Day 6 Left | 6 | 0
Day 7 Left | 6 | 0
| Feature ID |  | Description | Status | Notes
| SE |  | Create Recipe_step_detail.xml
| SE |  | Edit RecipeDetailActivity.java according to the mockup (use if else)
| SE |  | Add Exoplayer in build.gradle
| SE |  | Create Video player based on media playback lesson
| RA |  | See a device in fullscreen |  | https://stackoverflow.com/questions/46713761/how-to-play-video-full-screen-in-landscape-using-exoplayer
save instancestate in stepAct

## Sprint_03_Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2018-05-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
| Feature ID |  | Description | Status | Notes
| ST |  | add layout-sw600dp folder