## Product_Backlog
Product Name: | C1325 Library Management System | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Duy Nguyen
Initials: | DN
Student ID: | 10015102
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 3 |  | Total
Sprint 1 Left | 1 | 2 | 1
Sprint 2 Left | 1 | 0 | 2
Sprint 3 Left | 1 | 0 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
GA | 1 |  | 1 | Finished in Sprint 1 | User | see an grid arrangement of movie posters
CS | 2 |  | 1 | Finished in Sprint 1 | User | change sort via setting |  | most popular, top rated
TI | 3 |  | 2 |  | User | tapping into a poster and change to a new view | seeing more info | such as title, image,plot synopsis(overview in api), user rating (vote_average in api),resease date
[6 empty] | API KEY | ehi67z28dos8i6imcv7tyg6q
[6 empty] | Shared secret | 5ffajdn983
https://openapi.etsy.com/v2/listings/active?includes=Images&api_key=ehi67z28dos8i6imcv7tyg6q
https://openapi.etsy.com/v2/listings/active?tags=laptop&limit=12&includes=Images:1&api_key=ehi67z28dos8i6imcv7tyg6q
[6 empty] | Google Pay | https://developers.google.com/pay/api/android/guides/setup
[6 empty] | Google Identity | https://developers.google.com/identity/sign-in/android/
https://developers.google.com/identity/sign-in/android/start

## Sprint_01_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2018-05-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 14
Day 1 Left | 14 | 0
Day 2 Left | 14 | 0
Day 3 Left | 14 | 0
Day 4 Left | 14 | 0
Day 5 Left | 14 | 0
Day 6 Left | 14 | 0
Day 7 Left | 14 | 0
| Feature ID |  | Description | Status | Notes
| GA |  | Design main layout/Draw some mockups
| GA |  | Add recycler view dependency |  | See steps in notes and internet
| GA |  | Add Picasso dependency |  | sample from https://docs.google.com/document/d/1ZlN1fUsCSKuInLECcJkslIqvpKlP7jWL2TP9m6UiA6I/pub?embedded=true
| GA |  | Add recycler view in actitivity_main,xml
| GA |  | Create movie class for storing data/organizing data
| GA |  | Create row layout (What should be looked like in each grid) |  | Get sample from my mentor . Autofill grid manager
| GA |  | Create recycler view adapter |  | Get sample from my mentor . Autofill grid manager
| GA |  | Use Picasso to display poster images |  | sample from https://docs.google.com/document/d/1ZlN1fUsCSKuInLECcJkslIqvpKlP7jWL2TP9m6UiA6I/pub?embedded=true
| GA |  | Cretae Adapter (Display posters with mockup data first)
| GA |  | Connect with API (Usr the third library Retrofit) |  | http://api.themoviedb.org/3/movie/popular(top_rated)?api_key=/https://www.youtube.com/watch?v=R4XU8yPzSx0
| GA |  | Handle offline |  | https://stackoverflow.com/questions/1560788/how-to-check-internet-access-on-android-inetaddress-never-times-out
| CS |  | Create sortMenu.xml for sort list in menu folder
| CS |  | Create onCreateOptionMenu() & onOptionMenuSelected |  | See S04.01
| CS |  | Try to reset the API data for somehow |  | make sure manifest has the internet permission

## Sprint_02_Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2018-05-20 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-27
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 6
Day 1 Left | 5 | 1
Day 2 Left | 5 | 0
Day 3 Left | 5 | 0
Day 4 Left | 5 | 0
Day 5 Left | 5 | 0
Day 6 Left | 5 | 0
Day 7 Left | 5 | 0
| Feature ID |  | Description | Status | Notes
| TI |  | Create JSONUtils class for parsingJSON into movie class. |  | See previous project
| TI |  | Create JSONUtils class for parsingJSON into movie class. |  | See previous project
| TI |  | Create onclick listener for each poster image (toast first) | Completed Day 1 | toast.make
| TI |  | Create detailedActivity.java,.xml
| TI |  | Add detailedActivity in AndroidManifest.xml
| TI |  | Go back
TI

## Sprint_03_Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2018-05-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
| Feature ID |  | Description | Status | Notes
Included a WRITTEN test with each constructor and method!