## Product_Backlog
Product Name: | C1325 Library Management System | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Duy Nguyen
Initials: | DN
Student ID: | 10015102
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 5 |  | Total
Sprint 1 Left | 3 | 2 | 1
Sprint 2 Left | 1 | 2 | 2
Sprint 3 Left | 1 | 0 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
VT | 1 |  | 1 | Finished in Sprint 1 | User | view and play trailer (in youtube or web browser)
RR | 2 |  | 1 | Finished in Sprint 1 | User | read review of selected movie
MV | 3 |  | 2 | Finished in Sprint 2 | User | mark a movie as a favorite in detailed view |  | create the database and content provider to store the name and ids of the user's favorite movie
AS | 4 |  | 2 | Finished in Sprint 2 | User | Add show favorite collections in menu item
UM | 5 |  | 3 |  | User | Upgrade menuitems into prefernce segment

## Sprint_01_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2018-06-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-06-10
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 8 | 5
Day 2 Left | 4 | 4
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 4 | 0
| Feature ID |  | Description | Status | Notes
| VT |  | Add movie trailer portion in detailedActivity.xml | Completed Day 1
| VT |  | Create trailer class | Completed Day 1
| VT |  | Use retrofit to connect trailer class | Completed Day 1
| VT |  | Creare trailerAdapter | Completed Day 1
| VT |  | Create trailerHolder.xml and trailerHolder.java | Completed Day 1
| VT |  | Add implicit intent to open trailers in detailedActivity.java | Completed Day 2 | https://developer.android.com/guide/components/intents-common#Browser
| VT |  | Adjust detailedActivity.java. Think about logics based on API hints => | Completed Day 2 | http://api.themoviedb.org/3/movie/popular?api_key=84d34117b17f3abebe9d04a0325e21c6
| VT |  | Add intent filter in android manifest | Completed Day 2 | http://api.themoviedb.org/3/movie/{id}/videos?api_key=84d34117b17f3abebe9d04a0325e21c6
https://www.youtube.com/watch?v=Z5ezsReZcxU
http://api.themoviedb.org/3/review/{id}/videos?api_key=84d34117b17f3abebe9d04a0325e21c6
http://img.youtube.com/vi/<insert-youtube-video-id-here>/mqdefault.jpg
| RR |  | Add review portion in detailedActivi.xml | Completed Day 2
| RR |  | Add Load More in RecyclerViewAdapter(details how to do in the bottom) |  | https://medium.com/@programmerasi/how-to-implement-load-more-in-recyclerview-3c6358297f4
| RR |  | Add the loadingItem.xml for spinning icon |  | http://www.devexchanges.info/2017/02/android-recyclerview-dynamically-load.html
| RR |  | Define the interface for callbacks.Add onLoadMoreListenter. Java
| RR |  | Adjust recyclerview Adapter

## Sprint_02_Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2018-06-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-06-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 24
Day 1 Left | 24 | 0
Day 2 Left | 24 | 0
Day 3 Left | 24 | 0
Day 4 Left | 24 | 0
Day 5 Left | 24 | 0
Day 6 Left | 24 | 0
Day 7 Left | 24 | 0
| Feature ID |  | Description | Status | Notes
| MV |  | Add a button mark the movie as the favorite(floating action button)
| MV |  | Add contrract class implement BaseColumn |  | T07.4
| MV |  | Create DbHelper extend SQLiteDbHelper |  | T07.02
| MV |  | Add a method to add data in database |  | T07.05
| MV |  | Add a method to return cursor in MainActivity.java(get values from database)
| MV |  | Create a new RecyclerAdapter for showing favorite movies
| MV |  | Implement swapCursor method in Recycler Adapter |  | T07.05
| MV |  | Create a method to remove favorit movie(not necessary)
| MV |  | (option) send data to intent by using parcable
| MV |  | Create a new class for favorite intent
| MV |  | Create a content provider
| MV |  | Create a class that extend content provider and add onCreate method
| MV |  | Rgister content provider in the manifest
| MV |  | Define URI
| MV |  | Add that URI to the contract class
| MV | s | Build URI Matcher to match URI patterns to integers
| MV |  | Implement the required CRUID method
| MV |  | Insert: modifle contenprovider class and add onClickFavoriteButton to insert movie data |  | T09.4
| MV |  | Read: data from database: Use doInBackground from loader to get favorite movies data |  | T09.5
| MV |  | Delete :(optional- go back later if having time)
MV
| MV |  | Note: Don't forget to set notification of content resolver
| AS |  | Create new favorite.xml
| AS |  | Create new intent in mainActivity.java
| AS |  | Connect images with the database using reading func

## Sprint_03_Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2018-05-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 8 | 5
Day 2 Left | 4 | 4
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 4 | 0
| Feature ID |  | Description | Status | Notes
| MV |  | Add a button mark the movie as the favorite(floating action button) | Completed Day 1
| MV |  | Add ROOM dependencies in gradle | Completed Day 1
| MV |  | Anotate @enity and name database table as "movie" in movie class | Completed Day 1
| MV |  | Anotate id as @primaryKey in movie class | Completed Day 1
| MV |  | Create a constructor for movie | Completed Day 1
| MV |  | Note: if want to set column nmae use @ColumnInfo annotation
| MV |  | Create abstract class AppDataBase class with DAO abstract method without para | Completed Day 2 | T09.02B
| MV |  | call allowMainThreadQueries before building the instance(test purpose only) | Completed Day 2
| MV |  | Create a interface class with Dao annotation | Completed Day 2 | https://developer.android.com/training/data-storage/room/
| MV |  | Apply observer pattern in app with LiveData | Completed Day 2
Create the respos (put everything together)
Create the ViewModel
Update mainActivity to show favorite movies