## Product_Backlog
Product Name: | C1325 Library Management System | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Duy Nguyen
Initials: | DN
Student ID: | 10015102
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 19 |  | Total
Sprint 1 Left | 14 | 5 | 1
Sprint 2 Left | 9 | 5 | 2
Sprint 3 Left | 8 | 1 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
AP | 1 |  | 1 | Finished in Sprint 1 | Librarian | Add a publication | I can keep track of what is in the library
LP | 2 |  | 1 | Finished in Sprint 1 | Librarian | List all publications | I can find out what is in the library | This will also be needed for the next two features
CO | 3 |  | 1 | Finished in Sprint 1 | Librarian | Check out a publication | I can track who has borrowed each publication | Each publication will need to know if it is checked out or not
CI | 4 |  | 1 | Finished in Sprint 1 | Librarian | Check in a publication | I can tell when a publication is returned
HE | 5 |  | 1 | Finished in Sprint 1 | Librarian | Get help | I can learn how to use the system
PA | 6 |  | 1 |  | Librarian | Add a patron | I can conveniently keep track of all patrons | This is the Bonus level for Sprint #1
SP | 7 |  | 1 |  | Librarian | Select a patron when checking out a pub | I don't have to rekey recurring patron info | This is the Bonus level for Sprint #1
DMM | 8 |  | 2 | Finished in Sprint 2 | Librarian | Use a standard dialog for the main menu | I can interact more naturally with the system
DNP | 9 |  | 2 | Finished in Sprint 2 | Librarian | Use a series of dialogs for a new publication | I can interact more naturally with the system
DLP | 10 |  | 2 | Finished in Sprint 2 | Librarian | Use a stand dialog for the list of publications | I can interact more naturally with the system
DH | 11 |  | 2 | Finished in Sprint 2 | Librarian | Use dialogs for all other interaction (e.g., help) | I can interact more naturally with the system
DCO | 12 |  | 2 | Finished in Sprint 2 | Librarian | Use dialogs for check in and check out | I can interact more naturally with the system
DRM | 13 |  | 2 |  | Librarian | Add rich text to the main menu (dialog) | The menu is easier to navigate | This is the Bonus level for Sprint #2
DRH | 14 |  | 2 |  | Librarian | Add rich text to the help dialog | The help text is easier to understand | This is the Bonus level for Sprint #2
DCP | 15 |  | 2 |  | Librarian | Use a custom dialog to create new pubs | I can create them more quickly | This is the Extreme Bonus level for Sprint #2
MW | 16 |  | 3 | Finished in Sprint 3 | Librarian | Interact with a main window with drop-down menus | I can interact more naturally with the system | Replace the main menu dialog with a main window that is always visible
MT | 17 |  | 3 |  | Librarian | Add a toolbar to the main menu | I can more quickly access common features | This is the Bonus level for Sprint #3
MP | 18 |  | 3 |  | Librarian | Add a scrolling publications table to main window | I can more quickly look up publications | This is the Extreme Bonus level for Sprint #3
CU | 19 |  | 1 |  | Librarian | Add custom info for each publication type | I can keep better track of library assets | This is the Extreme Bonus level for Sprint #1

## Sprint_01_Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2018-02-22 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-03-01
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 28
Day 1 Left | 21 | 7
Day 2 Left | 15 | 6
Day 3 Left | 9 | 6
Day 4 Left | 8 | 1
Day 5 Left | 1 | 7
Day 6 Left | 1 | 0
Day 7 Left | 0 | 1
| Feature ID |  | Description | Status | Notes
| AP |  | Implement enums.h for age, genre, and media | Completed Day 1 | Included a WRITTEN test with each constructor and method!
| AP |  | Create a Publication class with data and a constructor | Completed Day 1
| AP |  | Add the to_string method to Publication | Completed Day 1
| AP |  | Add the is_checked_out method to Publication | Completed Day 1
| AP |  | Add the check_out method to Publication | Completed Day 1
| AP |  | Add the check_in method to Publication | Completed Day 1
| AP |  | Implement Publication regression test | Completed Day 1
| AP |  | Implement Invalid_transaction exception | Completed Day 2
| AP |  | Add the check_in method to Publication | Completed Day 2
| AP |  | Implement Library class with vector of publications | Completed Day 2
| AP |  | Implement Library::add_publication | Completed Day 2
| AP |  | Implement main menu | Completed Day 2
| AP |  | Implement main menu (1) Add publication | Completed Day 2
| LP |  | Implement Library::number_of_publications | Completed Day 3
| LP |  | Implement main menu (2) List all publications | Completed Day 3
| CO |  | Implement Library::check_out | Completed Day 3
| CO |  | Implement main menu (3) Check out publication | Completed Day 3
| CI |  | Implement Library::check_in | Completed Day 3
| CI |  | Implement main menu (4) Check in publication | Completed Day 3
| HE |  | Implement main menu (9) Help | Completed Day 4
| PA |  | Implement Patron class with constructor and getters | Completed Day 5
| PA |  | Implement Patron::to_string | Completed Day 5
| PA |  | Implement Patron class regression tests | Completed Day 5
| PA |  | Implement main menu (5) Add patron | Completed Day 5
| PA |  | Implement main menu (6) List patrons | Completed Day 5
| SP |  | Change from entering patron data to selecting patron on checkout | Completed Day 5
| SP |  | Update help file to cover management of patrons | Completed Day 5
| CU |  | Add and manage derived classes | Completed Day 7

## Sprint_02_Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2018-03-01 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-03-08
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 6 | 2
Day 2 Left | 2 | 4
Day 3 Left | 0 | 2
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
| Feature ID |  | Description | Status | Notes
| DMM |  | Add GTKFLAG in Make file | Completed Day 1 | Included a WRITTEN test with each constructor and method!
| DMM |  | Add Dialog.cpp Dialog.h | Completed Day 1
| DMM |  | Update input function in dialogs.cpp & .h to get numbers from users | Completed Day 2
| DMM |  | Create test_dialogs.cpp and update it in Makefile | Completed Day 2
| DMM |  | Edit cli in controller in fit gtkmm version | Completed Day 2
| DNP |  | Modify input dialogs.cpp to get limit through arguments | Completed Day 2
| DCO |  | Create select publication in view .cpp | Completed Day 3
| DH |  | Create dialogs for help function | Completed Day 3

## Sprint_03_Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2018-03-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-03-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 6 | 2
Day 2 Left | 0 | 6
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
| Feature ID |  | Description | Status | Notes
| MW |  | Add a vertical box container | Completed Day 1 | Included a WRITTEN test with each constructor and method!
| MW |  | Add a menu bar | Completed Day 1
| MW |  | Create a file menu and add to menu bar | Completed Day 2
| MW |  | Append Quit to file menu | Completed Day 2
| MW |  | Create a publication menu and add to menu bar | Completed Day 2
| MW |  | Append List,Add,Checkout,Checkin to publication menu | Completed Day 2
| MW |  | Create a Patron menu and add to menu bar | Completed Day 2
| MW |  | Append List,Add to publication menu | Completed Day 2