Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" / "Finished in Sprint 3" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
## Product Backlog
Product Name:	C1325 Library Management System					Complete Fields in Green!!!
Team ID:

Name:
Initials:
Student ID:

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	19		Total
Sprint 1 Left	11	8	1
Sprint 2 Left	3	8	2
Sprint 3 Left	0	3	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AP	1		1	Finished in Sprint 1	Librarian	Add a publication	I can keep track of what is in the library
LP	2		1	Finished in Sprint 1	Librarian	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3		1	Finished in Sprint 1	Librarian	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4		1	Finished in Sprint 1	Librarian	Check in a publication	I can tell when a publication is returned
HE	5		1	Finished in Sprint 1	Librarian	Get help	I can learn how to use the system
PA	6		1	Finished in Sprint 1	Librarian	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level for Sprint #1
SP	7		1	Finished in Sprint 1	Librarian	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level for Sprint #1
DMM	8		2	Finished in Sprint 2	Librarian	Use a standard dialog for the main menu	I can interact more naturally with the system
DNP	9		2	Finished in Sprint 2	Librarian	Use a series of dialogs for a new publication	I can interact more naturally with the system
DLP	10		2	Finished in Sprint 2	Librarian	Use a stand dialog for the list of publications	I can interact more naturally with the system
DH	11		2	Finished in Sprint 2	Librarian	Use dialogs for all other interaction (e.g., help)	I can interact more naturally with the system
DCO	12		2	Finished in Sprint 2	Librarian	Use dialogs for check in and check out	I can interact more naturally with the system
DRM	13		2	Finished in Sprint 2	Librarian	Add rich text to the main menu (dialog)	The menu is easier to navigate	This is the Bonus level for Sprint #2
DRH	14		2	Finished in Sprint 2	Librarian	Add rich text to the help dialog	The help text is easier to understand	This is the Bonus level for Sprint #2
DCP	15		2	Finished in Sprint 2	Librarian	Use a custom dialog to create new pubs	I can create them more quickly	This is the Extreme Bonus level for Sprint #2
MW	16		3	Finished in Sprint 3	Librarian	Interact with a main window with drop-down menus	I can interact more naturally with the system	Replace the main menu dialog with a main window that is always visible
MT	17		3	Finished in Sprint 3	Librarian	Add a toolbar to the main menu	I can more quickly access common features	This is the Bonus level for Sprint #3
MP	18		3	Finished in Sprint 3	Librarian	Add a scrolling publications table to main window	I can more quickly look up publications	This is the Extreme Bonus level for Sprint #3
CU	19		1	Finished in Sprint 1	Librarian	Add custom info for each publication type	I can keep better track of library assets	This is the Extreme Bonus level for Sprint #1
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Feb 22		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 01
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	28
Day 1 Left	21	7
Day 2 Left	15	6
Day 3 Left	9	6
Day 4 Left	8	1
Day 5 Left	1	7
Day 6 Left	1	0
Day 7 Left	0	1

	Feature ID		Description	Status	Notes
	AP		Implement enums.h for age, genre, and media	Completed Day 1	Includes a test with each constructor and method
	AP		Create a Publication class with data and a constructor	Completed Day 1
	AP		Add the to_string method to Publication	Completed Day 1	Useful for testing the class
	AP		Add the is_checked_out method to Publication	Completed Day 1
	AP		Add the check_out method to Publication	Completed Day 1
	AP		Add the check_in method to Publication	Completed Day 1
	AP		Implement Publication regression test	Completed Day 1
	AP		Implement Invalid_transaction exception	Completed Day 2
	AP		Add the check_in method to Publication	Completed Day 2
	AP		Implement Library class with vector of publications	Completed Day 2
	AP		Implement Library::add_publication	Completed Day 2
	AP		Implement main menu	Completed Day 2
	AP		Implement main menu (1) Add publication	Completed Day 2
	LP		Implement Library::number_of_publications	Completed Day 3
	LP		Implement main menu (2) List all publications	Completed Day 3
	CO		Implement Library::check_out	Completed Day 3
	CO		Implement main menu (3) Check out publication	Completed Day 3
	CI		Implement Library::check_in	Completed Day 3
	CI		Implement main menu (4) Check in publication	Completed Day 3
	HE		Implement main menu (9) Help	Completed Day 4
	PA		Implement Patron class with constructor and getters	Completed Day 5
	PA		Implement Patron::to_string	Completed Day 5
	PA		Implement Patron class regression tests	Completed Day 5
	PA		Implement main menu (5) Add patron	Completed Day 5
	PA		Implement main menu (6) List patrons	Completed Day 5
	SP		Change from entering patron data to selecting patron on checkout	Completed Day 5
	SP		Update help file to cover management of patrons	Completed Day 5
	CU		Add and manage derived classes	Completed Day 7
Sprint Burn Chart
Days
Tasks

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Mar 01		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 08
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	17
Day 1 Left	15	2
Day 2 Left	9	6
Day 3 Left	9	0
Day 4 Left	6	3
Day 5 Left	1	5
Day 6 Left	1	0
Day 7 Left	0	1

	Feature ID		Description	Status	Notes
	DMM		Create View::select_from_menu to enable main menu dialog	Completed Day 1	Included a WRITTEN test with each constructor and method!
	DMM		Set cmd to View::select_from_menu response	Completed Day 1
	DNP		Add View::select_{patron, genre, age, media} using dialogs	Completed Day 2
	DNP		Create View::get_{publications, patrons} to return string repr	Completed Day 2
	DNP		Replace cin/cout in controller.cpp for publication with Dialogs	Completed Day 2
	DLP		Replace loop with view.list_publications	Completed Day 2
	DLP		Reformat get_publications to better fit in the dialog	Completed Day 2
	DH		In View::help, replace cout with Dialogs::message	Completed Day 2
	DCO		Write View::select_publication and View::select_patron using dialogs	Completed Day 4
	DCO		Use View::select_publication and View::select_patron for check in	Completed Day 4
	DCO		Use View::select_publication and View::select_patron for check out	Completed Day 4
			Remove “using namespace std” and add “std::” to std namespace names	Completed Day 5
			Remove “201608” from all header guards	Completed Day 5
	DRM		Enable markup in Dialogs.cpp	Completed Day 5
	DRM		Add Pango markup to the menu text in view.cpp	Completed Day 5
	DRH		Add Pango markup to the help text in view.cpp	Completed Day 5
	DCP		Replace stream of dialogs in controller.cpp with a single custom dialog	Completed Day 7
Sprint Burn Chart
Days
Tasks

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Mar 08		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 22
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	16
Day 1 Left	13	3
Day 2 Left	10	3
Day 3 Left	7	3
Day 4 Left	6	1
Day 5 Left	5	1
Day 6 Left	4	1
Day 7 Left	0	4

	Feature ID		Description	Status	Notes
	MW		Add Main_window class with menu creation code	Completed Day 1	Baseline from Nim
	MW		Create pass-through handlers for menu items to controller.execute_cmd	Completed Day 1
	MW		Fix main() to create app and run Main_window instance	Completed Day 1
	MT		Add toolbar creation code to Main_window class	Completed Day 2
	MT		Find icons	Completed Day 2
	MT		Update About dialog to credit artists	Completed Day 2
	MP		Publication: Add to_strings method to extract every attribute in a vector<string>	Completed Day 3
	MP		Library: Add publication_to_strings to pass through to_strings from Publication	Completed Day 3
	MP		Controller: Add number_of_pubs and pub_to_strings methods	Completed Day 3
	MP		Main_window: Define nested Gtk::TreeModel::ColumnRecord class to specify columns	Completed Day 4
	MP		Main_window: Define Glib::RefPtr<Gtk::ListStore> as the Tree View to manage the data	Completed Day 5	Really should make Library a tree view, but that’s a bigger task
	MP		Main_window: Define Gtk::TreeView widget and Gtk::ScrolledWindow to scroll it	Completed Day 6
	MP		Main_window: Define add_row method to add a new row to the tree model	Completed Day 7
	MP		Main_window: Define update_rows to resync checkout data from library to tree model	Completed Day 7
	MP		Main_window: Add widgets to VBox in the constructor	Completed Day 7
	MP		Main_window: Update callbacks to sync data to tree model as the library changes	Completed Day 7
Sprint Burn Chart
Tasks
Days