Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product_Backlog
Product Name:	C1325 Library Management System					Complete Fields in Green!!!
Team ID:

Name:	Duy Nguyen
Initials:	DN
Student ID:	1001215102

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	8		Total
Sprint 1 Left	3	5	1
Sprint 2 Left	3	0	2
Sprint 3 Left	3	0	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AP	1		1	Finished in Sprint 1	Librarian	Add a publication	I can keep track of what is in the library
LP	2		1	Finished in Sprint 1	Librarian	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3		1	Finished in Sprint 1	Librarian	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4		1	Finished in Sprint 1	Librarian	Check in a publication	I can tell when a publication is returned
HE	5		1	Finished in Sprint 1	Librarian	Get help	I can learn how to use the system
PA	6		1		Librarian	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level
SP	7		1		Librarian	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level
CU	8		1		Librarian	Add custom info for each publication type	I can keep better track of library assets	This is the Extreme Bonus level
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Sep 21		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Sep 28
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	6	0
Day 5 Left	6	0
Day 6 Left	6	0
Day 7 Left	6	0

	Feature ID		Description	Status	Notes
	AP		Create a Publication class with data and a constructor		Includes a test with each constructor and method
	AP		Add the to_string method to Publication
	AP		Add the is_checked_out method to Publication
	AP		Add the check_out method to Publication
	AP		Add the check_in method to Publication
	LP		--> Add additional tasks to complete the homework
	CO
	CI
	HE
	PA
	SP
	CU
Sprint Burn Chart
Days
Tasks